## Slide 1: CommTest Project Develop Process (PDP) Training
Module 1 – PDP
4/19/2011

## Slide 2: Agenda
Goals of CommTest PDP
Scope
PDP Framework
Purpose of Gate
Gate Definitions
Roles & Responsibilities
Gate Reviews
Recommended Practices
Q&A

## Slide 3: Goals of CommTest PSDP
A common Product Development Process for all of CommTest to facilitate common processes and language allowing more consistent cross-functional and cross-site collaboration
A “Lean” and light weight policy document with flexible framework that can be scaled for very small to large projects and/or sites
A policy that enables progressive methods like Agile Software Development

## Slide 4: Scope
Who does it apply to
  All of CommTest new Product & Services Development
What projects does it apply to
  New Product Development including Services
  Derivative Products
    New features on existing products
    New options, i.e. low cost version
  Maintenance, sustaining, and the addition of minor new functionality efforts are at the discretion of the Product/Service Planning Gate Approver
What Projects may not Apply
  ECNs / CPs (ECRs, MCOs, etc.)
  Software patch release (dot releases) / bug fixes
  Management of Full Production and End of Life phases

## Slide 5: PSDP Framework
There maybe three levels in the PDP
  PDP top level document defines:
    Milestones (Gates)
    Deliverables at milestones
    Roles & responsibilities
    Governance of process
  Second level down defines “Functional Processes”
    Organizational processes associated with PDP
    Engineering, Marketing, Operations, Services, PMO
    Details of product development
    Deliverables for PDP
  A third level for local functional policies may be developed at the discretion of local management

## Slide 6: Purpose of Gates
Manage Investment Risk
Manage Customer Commitments
Assure Discipline
Assure Successful Completion of Project
Communicate Status
Quality, Cost, Schedule, Market Share, Financials
Achieve Resource Commitment

## Slide 7: Gate Definitions

## Slide 8: High Level PDP Flow
PC
PP Gate
PC Gate
PI Gate
IC Gate
FCS Gate
VP Gate
Initiation Phase
Proposal Phase
Planning Phase
Development Phase
Validation Phase
Ramp Up Phase
Launch Process
Launch Gate

## Slide 9: Project Charter (PC) – Not a Gate
The objective is to clearly establish the beginning of a development project and its objectives
The Project Charter shall consist of a brief document initiated by the responsible VP/GM or their designee containing:
  Notification to Program Manager & Stake Holders
  What the project/program is to accomplish
    Product concept
    Value proposition
  Frame the Business Rationale of Project/Program
    Investment
    Time frame
    Revenue
PC
PP Gate
PC Gate
PI Gate
IC Gate
FCS Gate
VP Gate
Initiation Phase
Proposal Phase
Planning Phase
Development Phase
Validation Phase
Ramp Up Phase

## Slide 10: Project Charter (PC) Deliverables
New product/service description
  Product/service concept
  Value proposition
Business rationale
  Strategic alignment
  Market opportunity
  Revenue target
  Project completion date
  Project spend expectations
Resources available to achieve Project Initiation

## Slide 11: Project Initiation (PI) Gate
The Project Initiation Gate occurs after the Initiation Phase
The objective of the Project Initiation Phase are:
  Align early team with the summary business goals from Project Charter (PC)
  Develop an initial risk summary
  Deliver a plan to achieve Project Proposal (PP). This includes:
    A schedule to PP and agreed resources
    A customer needs assessment plan
PC
PP Gate
PC Gate
PI Gate
IC Gate
FCS Gate
VP Gate
Initiation Phase
Proposal Phase
Planning Phase
Development Phase
Validation Phase
Ramp Up Phase

## Slide 12: Project Initiation (PI) Gate Deliverables
Plan to achieve PP (Program Proposal)
  Schedule to PP and agreed resources
  Customer needs assessment plan
  Elements of strategy alignment
Initial risk summary

## Slide 13: Project Proposal (PP) Gate
The Project Proposal Gate occurs after the Proposal Phase
The objectives of the Project Proposal Phase are:
  Validate the project business case
  Define product requirements
  Define product design targets
  Commit project resources to achieve next gate
PC
PP Gate
PC Gate
PI Gate
IC Gate
FCS Gate
VP Gate
Initiation Phase
Proposal Phase
Planning Phase
Development Phase
Validation Phase
Ramp Up Phase

## Slide 14: Project Proposal (PP) Gate Deliverables
PL Marketing
  Concept Review milestone
  Market assessment
  Customer assessment
  Competitive assessment
  Financial analysis
  Product/service positioning
  Market requirements document (MRD)
    Product/service configurations and options
  Demo pool plan
  Preliminary competitive IP assessment
Engineering
  High level architecture
  Draft Release Load Lineup or Software Rev
  High level scope of work
  Preliminary COGS
  Intellectual property
Operations
  Preliminary manufacturing and supply chain strategy.
Service
  Preliminary service strategy/TAC
Project Plan
  Skill & manpower requirements
  Project material/supplies
  Capital equipment
  Preliminary project cost
  Macro schedule
  Schedule to PC
  Committed resource plan to PC
  Key metrics (cost, performance, quality, etc.)
  Flexibility matrix
  Risks

## Slide 15: Project Commit (PC) Gate
The Project Commit Gate occurs after the Planning Phase
The objectives of the Planning Phase are:
  Develop a stable product definition
  Deliver the project plan
  Commit to deliver the product(s) and achieve the next 3 gates
PC
PP Gate
PC Gate
PI Gate
IC Gate
FCS Gate
VP Gate
Initiation Phase
Proposal Phase
Planning Phase
Development Phase
Validation Phase
Ramp Up Phase

## Slide 16: Project Commit (PC) Gate Deliverables
PL Marketing
  Marketing plan updated (from Project Proposal)
  Financial analysis
  Secure Customers between FCS and VP
GT Marketing
  Preliminary Launch Checklist
Engineering
  Functional specification complete (Non-Agile)
    Feature requirements breakdown
    Regulatory compliance requirements
    Environmental compliance requirements
    Manufacturability requirements
    Serviceability requirements
  Architecture and high level design complete
    Hardware, software, FPGA, mechanical
  Design qualification and product/service validation plan
  Updated Release Load Lineup and Software Rev
Operations
  Manufacturing plan complete
    Manufacturing metric targets
    Process flow diagrams
    Proto/pilot build schedule
    Manufacturing test plan (proto, pilot, production)
    Resource & capacity plan
    Preliminary ramp up plan
  Supply chain plan
Service
  Preliminary Service Plan/TAC complete
Project
  Project plan updated
  Project cost
  High confidence committed schedule to FCS
  Committed resources planned to Volume Production
  Plan Proto & pilot build quantity and allocation

## Slide 17: Integration Complete (IC) Gate
The Integration Complete Gate occurs after the Development Phase
The objectives of the Development Phase are:
  Validate complete product functionality
  Complete integration on the project
  Ensure the implementation is ready for product validation
PC
PP Gate
PC Gate
PI Gate
IC Gate
FCS Gate
VP Gate
Initiation Phase
Proposal Phase
Planning Phase
Development Phase
Validation Phase
Ramp Up Phase

## Slide 18: Integration Complete (IC) Gate Deliverables
PL Marketing
  Marketing business plan updated
  Financials updated
  Plan for order acceptance
  Beta tests arranged
GT Marketing
  Execution of Launch activities status
Engineering
  Designs complete (electrical, FPGA, software, mechanical)
  Prototypes built
  Hardware design verification testing complete
  Mechanical Design verification Complete
  Reliability testing complete
  Software unit and integration testing complete
  Hardware documentation released & pilot build authorized
  Draft customer documentation
  Validation plan and procedures complete
  Updated Release Load Lineup and Software Rev
Operations
  Proto build review complete
  Pilot material ordered
  Commit to plan to deliver the following for pilot build validation:
    Pilot manufacturing process
    Manufacturing readiness assessment
    DOF (Direct Order Fulfillment) validation plan
    Ramp up plan
Service
  Service Plan complete/reviewed
  Plan for First Customer Application (FCA)
Project
  Project plan updated
  Commit to VP date

## Slide 19: Launch Gate
PC
PP Gate
PC Gate
PI Gate
IC Gate
FCS Gate
VP Gate
Initiation Phase
Proposal Phase
Planning Phase
Development Phase
Validation Phase
Ramp Up Phase
Launch Process
Launch Gate
The Launch Gate occurs after the Launch Phase
The Launch Phase will typically begin with the completion of the PC Gate while the Launch Gate must complete prior to the First Customer Ship Gate
The objectives of the Launch Phase are:
  Ensure internal and external marketing collateral is produced
  Execute plan for demo and sales equipment
  Create pricing strategy and set price
  Develop training and support material

## Slide 20: Launch Gate Deliverables
GT Marketing
  Complete Launch Gate Template
  Launch is ready

## Slide 21: First Customer Ship (FCS) Gate
The First Customer Ship gate occurs after the Validation Phase
This is the first product deliverable to a customer for revenue
Non-revenue alpha, beta and demo units are permitted to be shipped to customers prior to FCS
The objectives of the Validation Phase are:
  Pilot build review complete demonstrating manufacturability
  All product verification has been completed
  Validate that a product that meets all published specifications
  Customer facing documentation available
  Ensure product quality meets customer expectations
  Authorize First Customer Shipment (FCS)
PC
PP Gate
PC Gate
PI Gate
IC Gate
FCS Gate
VP Gate
Initiation Phase
Proposal Phase
Planning Phase
Development Phase
Validation Phase
Ramp Up Phase

## Slide 22: First Customer Ship (FCS) Gate Deliverables
PL Marketing
  Marketing Business plan updated
GT Marketing
  Launch complete
Engineering
  Testing complete with results vs. plan
  Compliance testing complete –agency approvals achieved
  Software/firmware released
  User documentation released
  Engineering production documentation released
  Updated Release Load Lineup and Software Rev
Operations
    Pilot build review complete
    DOF product/service validation updated
    Ramp up plan updated
Service
  Service readiness complete
  Validate the delivery process from end to end
  Service Center Training/TAC underway
  Deployment team training complete
  FCA plan
Project
  Project plan updated
  Plan to Volume Production
    Schedule, resources & criteria
  Continuous improvement process initiated

## Slide 23: Volume Production (VP) Gate
The Volume Production Gate occurs after the Ramp-up Phase
The objectives for the Ramp-up Phase are:
  Ensure product, documentation and delivery process has been validated in a customer environment
  Demonstrate product and process stability targets and manufacturing capacity have been achieved
  Open design issues have been resolved
  Assure documentation and review of Lessons Learned during the project.
PC
PP Gate
PC Gate
PI Gate
IC Gate
FCS Gate
VP Gate
Initiation Phase
Proposal Phase
Planning Phase
Development Phase
Validation Phase
Ramp Up Phase

## Slide 24: Volume Production (VP) Gate Deliverables
PL Marketing
  Financial review
  Customer feedback review
GT Marketing
  Post Launch review
Engineering
  Tier 3 Customer Service team in place
  User documentation translated
  Updated Release Load Lineup and Software Rev
Operations
  Manufacturing ramp up
    Yield & statistics
    Standard COGS / costs review
    Manufacturing process implementation complete
    On time delivery & lead time
    Quality update
    DOF achieved
Service
  Status
    Service readiness
    Service Center/TAC training
    Deployment team training
Project
  Lessons learned
  Project close out
Continuous improvement report

## Slide 25: Roles and Responsibilities

## Slide 26: Program Manager
The Program Manager has the responsibility and authority to:
  Provide leadership and guidance to the Project Development team from Project Initiation through Volume Production
  Represent the project to Senior Management
  Secure resources to plan, design/develop, and introduce the new product(s)/platform
  Manage project to approved project objectives
  Escalate barriers and issues outside the project leadership team’s span of control
  Drives the successful completion of all gates

## Slide 27: Gate Approver
The Gate Approver for the PI, PP, FCS and VP gates is the Business Unit General Manager
The Gate Approver for the PC and IC gates is the CommTest Divisional VPs of R&D
The Launch Gate approver is the GT Marketing VP
The Gate Approver, or his/her designee, has the responsibility and authority to:
  Approve permanent or temporary delegation of Gate approval authority
  Provide leadership and guidance to the team
  Approve or deny gates

## Slide 28: Functional Leaders
Functional Leaders are responsible and have authority for:
  Executing to the requirements of their Functional Policy
  Representing their Function in the project
  Joint accountability for achieving the project goals
  Driving integrated project planning representing their function
  Driving implementation to plan

## Slide 29: Functional Resource Managers
Functional Resource Managers have the responsibility and authority to:
  Establish and implement functional policy that supports the framework provided by this policy
  Select functional leaders/project team members to represent their function
  Make resource and work commitments for functional activities
  Negotiate with the Program Manager if reallocation of project resources is anticipated

## Slide 30: Project Leadership Team / Extended Team
Project Leadership Team
  Consists of Program Managers and Functional Leads
Extended Team
  Execute the project deliverables
  Identifies risks
  Escalates issues to their Functional Team Leader

## Slide 31: Gate Reviewers
Gate Reviewers have the authority and responsibility to:
  Review and analyze the Gate Review Package.
  Identify issues with the project and providing feedback to the Program Manager and Functional Lead.
  Work with the Program Manager and Functional Lead to resolve issues

## Slide 32: Gate Reviews

## Slide 33: Review and Approval Process
Gate reviews are held by the Program Manager and the Gate Approver along with the Gate Reviewers
Decision is made by the Gate Approver on the current phase of the project
  Approved: The Gate Approver determines that Phase Objectives have been met
  Delayed Approval: The Gate Approver determines the Phase Objectives will be met when specifically identified criteria are met
  Approval Denied - Re-run the Review Cycle: The Gate Approver determines the Phase Objectives have not been met and identifies the specific issues
  Approval Denied - Program Stop: The Gate Approver determines that conditions warrant discontinuing the project. Funding stops
  (additional detail to the above in the PDP doc)

## Slide 34: Gate Management Guidance
Recommend Gate Review Package Distributed at Least Three (3) Business Days Prior to Gate Review Meeting
Recommend Questions to Gate Review Package be Submitted 24 Hours Prior to Gate Review Meeting
Gate Templates should be used, keep gate materials short and concise
During the Gate Review, the Program Manager provides a brief overview of the project status and addresses any open issues
It is the intention that the Gate Review should be a relatively brief meeting, not a project review
Attendance by reviewers is optional, but strongly requested

## Slide 35: Gate Management Policy
Gates may be combined with the agreement of the Gate Approver
A single project may have multiple Integration Complete and/or FCS/VP Gates
Program Manager may identify irrelevant Gate Deliverables as “Not Applicable”
At the request of the Program Manager and/or discretion of the Gate Approver, a Material Change Event will be cause to go back to the logical Gate to reset (re-gate) the project

## Slide 36: Recommended Practices
Always make certain you use the latest versions of the PDP from the SharePoint site at: http://milspapp1.ds.jdsu.net/sites/commtest/rsat/pdp2
Use the gate templates included in the PDP
Get the latest version of the Functional policies for your respective discipline from the SharePoint site above
  Functional Policies are required
Only collapse gates with support of impacted Gate Approvers

## Slide 37: Mike Fitzgerald Gordon Anderson Olivier Masselin Kurt McDaniel Steve Moss Jim Nerschook Brady Volpe Wally Wardak Wenli YU
If you have any questions, please contact any of the following originators of the PDP: